## Projects
Project ID | Project Name | Client ID | Project Manager | Region | Contract Value | Start Date | End Date | Status | Client Name
P001 | Bridge Alpha | C001 | James Carter | Midlands | 5200000 | 4602300% | 4632600% | Active | Network Rail
P002 | Water Main Bravo | C002 | Sarah Ahmed | South East | 3800000 | 4606800% | 4637100% | Active | Thames Water
P003 | Highway Charlie | C003 | Michael Green | North West | 6100000 | 4608200% | 4641800% | Active | National Highways
P004 | Rail Extension Delta | C001 | Emma Lewis | Midlands | 4700000 | 4612700% | 4647700% | Active | Network Rail
P005 | Flood Defence Echo | C004 | Daniel Hughes | South West | 2950000 | 4614300% | 4635600% | Planning | Environment Agency
22750000

## Clients
Client ID | Client Name | Contact Person | Email | Phone
C001 | Network Rail | David Smith | david.smith@networkrail.co.uk | 020 7946 1001
C002 | Thames Water | Emily Jones | emily.jones@thameswater.co.uk | 020 7946 1002
C003 | National Highways | Peter Brown | peter.brown@nationalhighways.co.uk | 020 7946 1003
C004 | Environment Agency | Lisa Taylor | lisa.taylor@environment-agency.gov.uk | 020 7946 1004

## Budget
Project ID | Category ID | Budget Amount | Cost Category
P001 | CAT01 | 1170000 | Labour
P001 | CAT02 | 1498000 | Materials
P001 | CAT03 | 608000 | Plant Hire
P001 | CAT04 | 796000 | Subcontractors
P001 | CAT05 | 187000 | Fuel & Transport
P001 | CAT06 | 281000 | Site Overheads
P001 | CAT07 | 140000 | Contingency
P002 | CAT01 | 958000 | Labour
P002 | CAT02 | 923000 | Materials
P002 | CAT03 | 513000 | Plant Hire
P002 | CAT04 | 547000 | Subcontractors
P002 | CAT05 | 171000 | Fuel & Transport
P002 | CAT06 | 205000 | Site Overheads
P002 | CAT07 | 103000 | Contingency
P003 | CAT01 | 1318000 | Labour
P003 | CAT02 | 1867000 | Materials
P003 | CAT03 | 769000 | Plant Hire
P003 | CAT04 | 878000 | Subcontractors
P003 | CAT05 | 220000 | Fuel & Transport
P003 | CAT06 | 274000 | Site Overheads
P003 | CAT07 | 164000 | Contingency
P004 | CAT01 | 1100000 | Labour
P004 | CAT02 | 1311000 | Materials
P004 | CAT03 | 592000 | Plant Hire
P004 | CAT04 | 719000 | Subcontractors
P004 | CAT05 | 169000 | Fuel & Transport
P004 | CAT06 | 212000 | Site Overheads
P004 | CAT07 | 127000 | Contingency
P005 | CAT01 | 611000 | Labour
P005 | CAT02 | 770000 | Materials
P005 | CAT03 | 425000 | Plant Hire
P005 | CAT04 | 478000 | Subcontractors
P005 | CAT05 | 133000 | Fuel & Transport
P005 | CAT06 | 159000 | Site Overheads
P005 | CAT07 | 79000 | Contingency

## Cost_Categories
Category ID | Cost Category
CAT01 | Labour
CAT02 | Materials
CAT03 | Plant Hire
CAT04 | Subcontractors
CAT05 | Fuel & Transport
CAT06 | Site Overheads
CAT07 | Contingency

## Actual_Cost
cat | Invoice No | Project ID | Project Name | Category ID | Cost Category | Supplier | Description | Amount | Month
4603000% | INV-1001 | P001 | Bridge Alpha | CAT02 | Materials | Midland Steel Ltd | Reinforcement steel | 185000 | 2026-01-01
4603700% | INV-1002 | P001 | Bridge Alpha | CAT01 | Labour | BuildForce Labour | January site labour | 98000 | 2026-01-01
4604400% | INV-1003 | P001 | Bridge Alpha | CAT03 | Plant Hire | Heavy Plant Hire Ltd | Excavator hire | 46000 | 2026-01-01
4605800% | INV-1004 | P001 | Bridge Alpha | CAT02 | Materials | Concrete Solutions | Structural concrete | 142000 | 2026-02-01
4607100% | INV-1005 | P001 | Bridge Alpha | CAT04 | Subcontractors | Apex Structures | Specialist steel installation | 125000 | 2026-02-01
4609100% | INV-1006 | P001 | Bridge Alpha | CAT01 | Labour | BuildForce Labour | February and March labour | 185000 | 2026-03-01
4609800% | INV-1007 | P001 | Bridge Alpha | CAT05 | Fuel & Transport | UK Fuel Services | Diesel and transport | 32000 | 2026-03-01
4611600% | INV-1008 | P001 | Bridge Alpha | CAT06 | Site Overheads | SiteSafe Services | Site accommodation and security | 48000 | 2026-04-01
4607400% | INV-2001 | P002 | Water Main Bravo | CAT01 | Labour | Aqua Civil Labour | Initial site labour | 76000 | 2026-02-01
4608100% | INV-2002 | P002 | Water Main Bravo | CAT03 | Plant Hire | Excavation Plant UK | Trenching equipment | 68000 | 2026-02-01
4609300% | INV-2003 | P002 | Water Main Bravo | CAT02 | Materials | PipeWorks UK | Water pipes | 154000 | 2026-03-01
4610600% | INV-2004 | P002 | Water Main Bravo | CAT04 | Subcontractors | Utility Specialists Ltd | Specialist installation work | 92000 | 2026-03-01
4612100% | INV-2005 | P002 | Water Main Bravo | CAT01 | Labour | Aqua Civil Labour | March labour | 87000 | 2026-04-01
4612800% | INV-2006 | P002 | Water Main Bravo | CAT05 | Fuel & Transport | Fleet Transport UK | Fuel and delivery | 27000 | 2026-04-01
4608600% | INV-3001 | P003 | Highway Charlie | CAT02 | Materials | RoadStone Materials | Aggregates | 265000 | 2026-03-01
4609900% | INV-3002 | P003 | Highway Charlie | CAT03 | Plant Hire | Highway Plant Hire | Road rollers and plant | 116000 | 2026-03-01
4611400% | INV-3003 | P003 | Highway Charlie | CAT01 | Labour | Northern Civils Labour | March labour | 123000 | 2026-04-01
4612600% | INV-3004 | P003 | Highway Charlie | CAT02 | Materials | Asphalt Direct | Asphalt materials | 194000 | 2026-04-01
4614100% | INV-3005 | P003 | Highway Charlie | CAT04 | Subcontractors | RoadMark Contractors | Specialist road works | 138000 | 2026-04-01
4615000% | INV-3006 | P003 | Highway Charlie | CAT05 | Fuel & Transport | Northern Fuel Ltd | Fuel | 41000 | 2026-05-01
4613200% | INV-4001 | P004 | Rail Extension Delta | CAT01 | Labour | RailBuild Workforce | Initial labour | 94000 | 2026-04-01
4614000% | INV-4002 | P004 | Rail Extension Delta | CAT02 | Materials | Track Materials UK | Rail materials | 172000 | 2026-04-01
4614800% | INV-4003 | P004 | Rail Extension Delta | CAT03 | Plant Hire | Rail Plant Hire Ltd | Specialist machinery | 88000 | 2026-05-01
4616100% | INV-4004 | P004 | Rail Extension Delta | CAT04 | Subcontractors | Rail Systems Ltd | Signalling preparation | 105000 | 2026-05-01
4615100% | INV-5001 | P005 | Flood Defence Echo | CAT01 | Labour | FloodWorks Labour | Site preparation labour | 62000 | 2026-05-01
4615800% | INV-5002 | P005 | Flood Defence Echo | CAT03 | Plant Hire | Earthworks Plant Ltd | Earthmoving equipment | 74000 | 2026-05-01
4616500% | INV-5003 | P005 | Flood Defence Echo | CAT04 | Subcontractors | Environmental Civils Ltd | Specialist flood works | 83000 | 2026-05-01
4617200% | INV-5004 | P005 | Flood Defence Echo | CAT02 | Materials | Barrier Systems UK | Flood barrier materials | 121000 | 2026-05-01
Formulas:
Month = EOMONTH(tblActualCosts[[#This Row],[cat]],-1)+1

## Cost_Reconciliation
Project ID | Project Name | Contract Value | Cost Budget | Planned Margin | Margin % | Actual Spend | Remaining Budget | Budget Used %
P001 | Bridge Alpha | 5200000 | 4680000 | 520000 | 10% | 861000 | 3819000 | 18.4%
P002 | Water Main Bravo | 3800000 | 3420000 | 380000 | 10% | 504000 | 2916000 | 14.74%
P003 | Highway Charlie | 6100000 | 5490000 | 610000 | 10% | 877000 | 4613000 | 15.97%
P004 | Rail Extension Delta | 4700000 | 4230000 | 470000 | 10% | 459000 | 3771000 | 10.85%
P005 | Flood Defence Echo | 2950000 | 2655000 | 295000 | 10% | 340000 | 2315000 | 12.81%
Total |  | 22750000 | 20475000 | 2275000 |  | 3041000 | 17434000

## Variance_Analysis
Project ID | Project Name | Category ID | Cost Category | Budget | Actual Cost | Remaining Budget | Budget Used % | Variance Status
P001 | Bridge Alpha | CAT01 | Labour | 1170000 | 283000 | 887000 | 24.19% | Within Budget
P001 | Bridge Alpha | CAT02 | Materials | 1498000 | 327000 | 1171000 | 21.83% | Within Budget
P001 | Bridge Alpha | CAT03 | Plant Hire | 608000 | 46000 | 562000 | 7.566% | Within Budget
P001 | Bridge Alpha | CAT04 | Subcontractors | 796000 | 125000 | 671000 | 15.7% | Within Budget
P001 | Bridge Alpha | CAT05 | Fuel & Transport | 187000 | 32000 | 155000 | 17.11% | Within Budget
P001 | Bridge Alpha | CAT06 | Site Overheads | 281000 | 48000 | 233000 | 17.08% | Within Budget
P001 | Bridge Alpha | CAT07 | Contingency | 140000 | 0 | 140000 | 0% | Within Budget
P002 | Water Main Bravo | CAT01 | Labour | 958000 | 163000 | 795000 | 17.01% | Within Budget
P002 | Water Main Bravo | CAT02 | Materials | 923000 | 154000 | 769000 | 16.68% | Within Budget
P002 | Water Main Bravo | CAT03 | Plant Hire | 513000 | 68000 | 445000 | 13.26% | Within Budget
P002 | Water Main Bravo | CAT04 | Subcontractors | 547000 | 92000 | 455000 | 16.82% | Within Budget
P002 | Water Main Bravo | CAT05 | Fuel & Transport | 171000 | 27000 | 144000 | 15.79% | Within Budget
P002 | Water Main Bravo | CAT06 | Site Overheads | 205000 | 0 | 205000 | 0% | Within Budget
P002 | Water Main Bravo | CAT07 | Contingency | 103000 | 0 | 103000 | 0% | Within Budget
P003 | Highway Charlie | CAT01 | Labour | 1318000 | 123000 | 1195000 | 9.332% | Within Budget
P003 | Highway Charlie | CAT02 | Materials | 1867000 | 459000 | 1408000 | 24.58% | Within Budget
P003 | Highway Charlie | CAT03 | Plant Hire | 769000 | 116000 | 653000 | 15.08% | Within Budget
P003 | Highway Charlie | CAT04 | Subcontractors | 878000 | 138000 | 740000 | 15.72% | Within Budget
P003 | Highway Charlie | CAT05 | Fuel & Transport | 220000 | 41000 | 179000 | 18.64% | Within Budget
P003 | Highway Charlie | CAT06 | Site Overheads | 274000 | 0 | 274000 | 0% | Within Budget
P003 | Highway Charlie | CAT07 | Contingency | 164000 | 0 | 164000 | 0% | Within Budget
P004 | Rail Extension Delta | CAT01 | Labour | 1100000 | 94000 | 1006000 | 8.545% | Within Budget
P004 | Rail Extension Delta | CAT02 | Materials | 1311000 | 172000 | 1139000 | 13.12% | Within Budget
P004 | Rail Extension Delta | CAT03 | Plant Hire | 592000 | 88000 | 504000 | 14.86% | Within Budget
P004 | Rail Extension Delta | CAT04 | Subcontractors | 719000 | 105000 | 614000 | 14.6% | Within Budget
P004 | Rail Extension Delta | CAT05 | Fuel & Transport | 169000 | 0 | 169000 | 0% | Within Budget
P004 | Rail Extension Delta | CAT06 | Site Overheads | 212000 | 0 | 212000 | 0% | Within Budget
P004 | Rail Extension Delta | CAT07 | Contingency | 127000 | 0 | 127000 | 0% | Within Budget
P005 | Flood Defence Echo | CAT01 | Labour | 611000 | 62000 | 549000 | 10.15% | Within Budget
P005 | Flood Defence Echo | CAT02 | Materials | 770000 | 121000 | 649000 | 15.71% | Within Budget
P005 | Flood Defence Echo | CAT03 | Plant Hire | 425000 | 74000 | 351000 | 17.41% | Within Budget
P005 | Flood Defence Echo | CAT04 | Subcontractors | 478000 | 83000 | 395000 | 17.36% | Within Budget
P005 | Flood Defence Echo | CAT05 | Fuel & Transport | 133000 | 0 | 133000 | 0% | Within Budget
P005 | Flood Defence Echo | CAT06 | Site Overheads | 159000 | 0 | 159000 | 0% | Within Budget
P005 | Flood Defence Echo | CAT07 | Contingency | 79000 | 0 | 79000 | 0% | Within Budget
Total |  |  |  | 20475000 | 3041000 | 17434000 | 14.85%

## Pivot_Analysis
Month | Sum of Amount
01-Apr | 883000
01-Mar | 844000
01-May | 574000
01-Feb | 411000
01-Jan | 329000
Grand Total | 3041000
Project Name | (All)
3041000
Cost Category | Sum of Amount
Materials | 1233000 | 100000 | 3.288%
Labour | 725000 | 725000 | 23.84%
Subcontractors | 543000 | 1233000 | 40.55%
Plant Hire | 392000 | 392000 | 12.89%
Fuel & Transport | 100000 | 48000 | 1.578%
Site Overheads | 48000 | 543000 | 17.86%
Grand Total | 3041000
Project Name | (All)
Supplier | Sum of Amount
Track Materials UK | 172000
Midland Steel Ltd | 185000
Asphalt Direct | 194000
RoadStone Materials | 265000
BuildForce Labour | 283000
Grand Total | 1099000
Row Labels | Count of Project ID
P001 | 1
P002 | 1
P003 | 1
P004 | 1
P005 | 1
Grand Total | 5
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard (hidden)
Commercial Cost Dashboard
Reporting Period: January 2026 - May 2026
Total Contract Value | Total Cost Budget | Actual Spend | Remaining Budget | Planned Margin | Budget Used %
22750000 | 20475000 | 3041000 | 17434000 | 2275000 | 14.85%
Highest Spend Category | Highest Spend Month | Largest Supplier | Project Active
Materials | 01-Mar | Track Materials UK | 5
1233000 | 883000 | 283000
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard_data
KPI | Formula
Total Contract Value | 22750000
Total Budget | 20475000
Actual Spend | 3041000
Remaining Budget | 17434000
Planned Margin | 2275000
Budget Used % | 14.85%
Highest Spend Category | Materials
Highest Spend Month | 01-Mar
Largest Supplier | Track Materials UK
Projects Active | 5
Budget available % | 85.15%
project ID | Project | Budget | Actual | budget used % | Status
P001 | Bridge Alpha | 4680000 | 861000 | 18.4% | On Track
P002 | Water Main Bravo | 3420000 | 504000 | 14.74% | On Track
P003 | Highway Charlie | 5490000 | 877000 | 15.97% | On Track
P004 | Rail Extension Delta | 4230000 | 459000 | 10.85% | On Track
P005 | Flood Defence Echo | 2655000 | 340000 | 12.81% | On Track
Project | Status | Budget used | Manager
Bridge Alpha | On Track | 18.4% | James Carter
Water Main Bravo | On Track | 14.74% | Sarah Ahmed
Highway Charlie | On Track | 15.97% | Michael Green
Rail Extension Delta | On Track | 10.85% | Emma Lewis
Flood Defence Echo | On Track | 12.81% | Daniel Hughes
dd

## Dashboard II
Joseph Gallagher Group Commercial Cost Dashboard
Reporting Period: January 2026 - May 2026
Project | Status | Budget Used % | Manager
Bridge Alpha | On Track | 18.4% | James Carter
Water Main Bravo | On Track | 14.74% | Sarah Ahmed
Highway Charlie | On Track | 15.97% | Michael Green
Rail Extension Delta | On Track | 10.85% | Emma Lewis
Flood Defence Echo | On Track | 12.81% | Daniel Hughes
Filters
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Total Contract Value
£22.75M
Portfolio Value
Total Cost Budget
£20.48M
Approved Budget
Actual Spend
£3.04M
14.9%
Utilised
Remaining Budget
£17.43M
85.1%
Availbale
Planned Margins
£2.28M
Active Projects
5
Current Portfolio
10% Target
COMMERCIAL INSIGHTS
• Materials account for 40.5% of portfolio spend.
• BuildForce Labour remains the largest supplier (£283k).
• Overall portfolio utilisation is 14.9%.
• No projects currently exceed budget.